## Security Clause Checklist
Clause Category | Description | Present? | Strength | Action Needed
Data Protection & GDPR | Defines roles, lawful basis, includes Data Processing Agreement | Yes | Strong | None
Information Security | Requires alignment with ISO 27001 or equivalent | Yes | Medium | Add reference to certification validity
Incident Notification | Defines breach notification within 72 hours | No | Weak | Add specific notification window
Confidentiality & NDAs | Covers proprietary and customer data | Yes | Strong | None
Access Control / MFA | Defines authentication & password standards | Yes | Medium | Clarify MFA enforcement
Audit & Inspection Rights | Allows Marymia Ltd to audit vendor security | No | Missing | Insert audit clause
Subprocessor Management | Requires written approval before subcontracting | Yes | Medium | Add explicit consent clause
Business Continuity / DR | Requires tested DR plan and backup schedule | Yes | Medium | Attach BCP annex
Termination for Breach | Allows termination for non-compliance | Yes | Strong | None

## Vendor Contract Review Matrix
Vendor | Risk Rating | Gaps Identified | Priority | Reviewer | Status
DHL Logistics | High | No incident clause, no audit rights | Critical | I. Adedeji | Open
Zoom Communications | Medium | Weak subprocessor clause | High | Compliance | In progress
FedEx Delivery | Medium | No breach notification clause | High | Legal | Open
AWS Cloud Services | Low | Fully compliant | N/A | Risk Analyst | Closed
QuickBooks (Intuit) | Low | Minor BCP evidence gap | Medium | Procurement | Closed

## Clause Improvement Log
Clause | Weakness | Recommended Improvement | Owner | Deadline
Incident Notification | Absent from DHL contract | Add 72-hour notification clause | Legal | 20-Jul-2024
Audit Rights | Missing in FedEx agreement | Include right-to-audit clause | Procurement | 25-Jul-2024
Subprocessor Management | Weak wording | Require prior written consent | Compliance | 30-Jul-2024
Business Continuity | Vague reference | Attach BCP and annual DR report | Risk Analyst | 31-Jul-2024

## Stakeholder Engagement
Stakeholder | Role | Engagement Outcome
Legal Counsel | Reviews & drafts contract language | Approved addition of audit and breach clauses
Procurement Manager | Tracks renewal cycles and signatures | Coordinated DHL and FedEx addendums
Compliance Manager | Ensures GDPR and ISO 27001 alignment | Confirmed updated DPA annex
Risk Committee | Final approval of contract changes | Signed off all high-priority amendments