## Risk Treatment Plan
Vendor | Risk Rating | Key Issue | Treatment Option | Mitigation Actions | Owner | Target Date | Status
DHL Logistics | High | No incident response plan, no audit rights | Mitigate / Transfer | Require IR plan and insert audit clause into contract | Legal / Compliance | 30-Jul-2024 | In progress
Zoom Communications | Medium | Expired ISO 27001 certificate | Mitigate | Request updated certificate and subprocessor list | Risk Analyst | 25-Jul-2024 | Open
FedEx Delivery | Medium | No breach notification clause | Mitigate / Transfer | Add 72-hour breach clause and DPA annex | Legal | 30-Jul-2024 | Open
AWS Cloud Services | Low | No material gaps | Accept | Maintain annual review cadence | Compliance | 31-Dec-2024 | Closed
QuickBooks (Intuit) | Low | Minor BCP clause gaps | Mitigate | Request DR test summary and RTO/RPO evidence | Procurement | 01-Aug-2024 | In progress

## Vendor Risk Register
Risk ID | Vendor | Description | Likelihood (1-3) | Impact (1-3) | Risk Score (=Likelihood*Impact) | Risk Level (Auto) | Action | Status
R01 | DHL Logistics | Missing incident response plan / no audit rights | 3 | 3 |  |  | Mitigate | In progress
R02 | Zoom Communications | Outdated ISO certificate | 2 | 3 |  |  | Mitigate | Open
R03 | FedEx Delivery | No data breach notification clause / no DPA | 2 | 4 |  |  | Transfer | Open
R04 | QuickBooks (Intuit) | Weak BCP evidence | 1 | 3 |  |  | Mitigate | In progress
R05 | AWS Cloud Services | Minor internal process delay | 1 | 2 |  |  | Accept | Closed

## Management Summary
Metric | Value | Notes
Vendors Reviewed | 30 | 30 in-scope third parties under active contract
High-Risk Vendors | 2 | DHL Logistics, FedEx Delivery
Medium-Risk Vendors | 3 | Zoom, QuickBooks, (monitor FedEx post-remediation)
Low-Risk Vendors | 25 | AWS, etc. All have sufficient controls
Treatment Completion % | 80% | 24/30 vendors remediated or formally accepted
Next Portfolio Review Date | 20-Jan-2025 | 6-month recurring review cycle

## Version Control
Version | Date | Prepared By | Reviewed By | Approved By | Notes
1.0 | 20-Jul-2024 | Ikuomola Adedeji – Third-Party Risk Analyst | Compliance Manager | Risk Committee | Initial release