## KRI Library
KRI | Definition | Data Source | Tier (Default) | Amber Threshold (Text) | Red Threshold (Text) | Default Severity (Auto) | Owner | Action (Playbook)
Cert Status | ISO/SOC2 certificate validity period | Certificate / Registry | Tier 1-2 | <90 days | Expired | Amber | Compliance | Request updated cert/bridge letter
Breach/Incident Signal | Public or vendor-reported incident | Vendor Notice / News | Tier 1 | Suspected | Confirmed | Red | Legal | Trigger incident playbook + exec update
BCP/DR Testing | Annual DR test evidence and results | DR Report | Tier 1 | >12 months | >18 months or failed | Amber | Risk | Request test + results; verify RTO/RPO
Subprocessor Changes | New or changed sub-processors | Vendor Register | Tier 1-2 | Notice <30d | No notice | Amber | Compliance | Enforce notice + DPA update
MFA Coverage | Privileged account MFA coverage % | Screenshot/Report | Tier 3 | <95% | <85% | Green | IT Security | Action plan; re-test in 30 days
Vuln Mgmt SLA | Time to remediate critical vulns | Attestation/Report | Tier 1-2 | >30 days | >60 days | Amber | Sec Eng | Remediation plan; contract credits
Support SLA Breach | Security ticket SLA breaches | Ticket Metrics | Tier 2-3 | 1/quarter | >=2/quarter | Green | Vendor Mgr | Service review + corrective actions
Privacy Requests SLA | DSAR/erasure turnaround time | Vendor Log | Tier 1-2 | >25 days | >30 days | Green | DPO | Escalate to DPO; tighten workflow
Logging & SIEM | Audit logging and monitoring coverage | Attestation | Tier 1 | Partial coverage | No central logging | Amber | Sec Eng | Implement SIEM / improve coverage
Encryption at Rest | Encryption for stored customer data | Policy/Evidence | Tier 1 | Legacy systems | No encryption | Red | Compliance | Contractual requirement + technical plan

## Monitoring Register
Date | Vendor | Tier | Event Type | KRI Impacted | Evidence Location | Severity (Auto from KRI) | Action | Owner | Due Date | Status
10-Jul-2024 | AWS Cloud Services | Tier 1 | DR Test review | BCP/DR Testing | Evidence/AWS/DR2024 |  | Record for monthly summary | Risk Analyst |  | Closed
12-Jul-2024 | Zoom Communications | Tier 2 | Certificate expiry in 60d | Cert Status | VendorDocs/ZoomCert |  | Request bridge letter | Compliance | 20-Jul-2024 | Open
14-Jul-2024 | DHL Logistics | Tier 1 | Security incident (minor) | Breach/Incident Signal | News/DHLIncident |  | Trigger breach playbook + legal review | Legal | 17-Jul-2024 | In Progress
16-Jul-2024 | FedEx Delivery | Tier 2 | Audit rights missing | Subprocessor Changes | Contracts/FedEx2024 |  | Legal addendum update | Procurement | 25-Jul-2024 | In Progress
18-Jul-2024 | QuickBooks (Intuit) | Tier 3 | Routine KRI review | MFA Coverage | Logs/Quickbooks |  | No action required | Risk Analyst |  | Closed

## Escalation & Runbook
Severity | Response Time | Notification Path | Responsible Stakeholders | Escalation Level | Required Action
Green | Track only | TPRM Analyst | Risk Team | None | Log event in monthly brief
Amber | 48 hours | Compliance + Manager | Risk + Compliance | Level 1 | Corrective action plan + follow-up
Red | 24 hours | Risk Committee + Exec | Legal + Exec + Risk | Level 2 | Incident report, containment, daily updates

## Monthly Risk Brief
Metric | Value | Comments
Open Actions |  | Across all vendors
Red Alerts |  | Triggered KRIs requiring exec visibility
Amber Alerts |  | KRIs requiring owner action
Green Checks |  | Routine monitoring
Vendors in Scope | 5 | AWS, Zoom, DHL, FedEx, QuickBooks
Expiring Certificates (90d) | Zoom | From Monitoring Register events

## Version Control
Field | Value
Document Title | Marymia Ltd – Continuous Monitoring & KRI Oversight Workbook
Version | 1.0
Prepared by | Ikuomola Adedeji – Third-Party Risk Analyst
Reviewed by | Compliance Manager
Approved by | Risk Committee
Date | 25-Jul-2024