## Incident Summary & Timeline
Marymia Ltd – Third-Party Incident (Tabletop)
Field | Value | Field | Value | Field | Value
Incident ID | IR-TPRM-2024-007 | Vendor |  | Tier
Service | Video Conferencing & Cloud Recordings | KRI Impacted |  | Detection Date
Severity (Linked) |  | Status |  | Owner | Ikuomola Adedeji
Root Cause | Vendor API permissions misconfigured during maintenance | Data Impact | HR meeting titles and 15 recordings (possible PII) | ICO Consideration | Yes - Draft notification prepared
Description | API misconfiguration exposed meeting metadata and recording links for some enterprise tenants.
Time | Event | Owner | Evidence | Status
09:15 | News report detected via Monitoring | TPRM Analyst | News/Zoom_Leak | Done
09:45 | Vendor advisory received | Compliance | Advisory.pdf | Done
10:20 | HR recordings identified | DPO | HR_Recording_List.xlsx | In Progress
10:45 | ICO assessment started | Legal | ICO_Draft.docx | Open

## Decision Log
Time | Decision | Rationale | Owner | Evidence | Severity | Status | Urgency (Auto)
09:40 | Treat as suspected personal data breach | HR recordings may include PII | DPO | HR evidence path | Red | Closed
10:10 | Apply emergency sharing restrictions | Prevent recurrence while vendor fixes | IT Sec | Policy screenshot | Amber | In Progress
10:50 | Prepare ICO notification draft | GDPR Art.33 72-hour window | Legal | ICO template | Red | Open

## Evidence Register
Evidence Name | Type | Source | Verified (Y/N) | Linked Risk ID | Verification Date | Reviewer | Comments | Severity (Auto)
Vendor Advisory | Email | Vendor | Yes | R-TPRM-006 | 23-Jul-2024 | Compliance | Verified official
HR Recording List | Internal | HR | Yes | R-TPRM-007 | 23-Jul-2024 | DPO | Confirmed affected
ICO Draft | Document | Legal | No | R-TPRM-008 |  | Legal | Awaiting review

## Post-Incident Report
Section | Content (Editable)
Executive Summary | What happened, impact, status.
Root Cause | Vendor API misconfiguration; exposure path summary.
Impact Assessment | Data types, volume, roles, regulatory angle (GDPR Art.33/34).
Timeline | Summarise key events from Incident Summary sheet.
Controls & Containment | Emergency sharing policy; DLP updates; SSO enforcement.
Vendor Performance | Timeliness, quality of comms, evidence supplied.
Actions & Owners | See Lessons Learned sheet.
Lessons Learned | Control + contract improvements to prevent recurrence.

## Lessons Learned & Actions
Action | Owner | Due | Status | Severity | Dependency | On Track? (Auto)
Add 24h breach clause to vendor contract | Legal | 31-Jul-2024 | In Progress | Amber | Contract
Force SSO for all meetings | IT Sec | 28-Jul-2024 | Closed | Green | Policy
Add KRI 'External recording links detected' | Risk | 05-Aug-2024 | Open | Amber | Monitoring
Conduct vendor revalidation audit | TPRM | 10-Aug-2024 | Planned | Green | Vendor review
Formulas:
On Track? (Auto) = IF(OR([Status]="Closed",TODAY()<=[Due]),"On Track","Overdue")

## Version Control
Field | Value
Document Title | Marymia Ltd – Module 7: Incident Simulation & Lessons Learned Workbook
Version | 1.0
Prepared by | Ikuomola Adedeji – Third-Party Risk Analyst
Linked Source | MarymiaLtd_Module6_ContinuousMonitoring.xlsx
Approved by | Risk Committee
Date | 25-Jul-2024